## Sheet1
Feature | Initial Estimate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Hours Left
Categories | 60 | 20 | 8 | 5 | 1 | 5 | 10 | 0 | 1 | 10
Synchronization | 60 | 10 | 5 | 2 | 2 | 5 | 10 | 19 | 2 | 5
Acccounts | 60 | 5 | 8 | 2 | 10 | 5 | 10 | 5 | 10 | 5
Reminders | 60 | 10 | 12 | 2 | 3 | 5 | 10 | 2 | 10 | 6
Settting | Start | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Geplande Uuren |  | 8 | 8 | 8 | 8 | 8 | TBA | TBA | TBA
Werkende Uuren |  | 3 | 8 | - | - | TBA | TBA | TBA | TBA
Remaining Effort | 240 | 0 | -8 | 8 | 8 | TBA | TBA | TBA | TBA
Ideal Burndown | 240 | 0 | -8 | 0 | -8 | TBA | TBA | TBA | TBA